## ABOVE_HAL Patches
PROJECT/PATH | PATCH NAME | COMPONENT | CATEGORY | FT Contact | Proposed FT Contact | Comments
frameworks/base | 0113-PORT-FROM-MAIN-JellyBean-Enable-WiDi-support-in-Audi.patch | widi | Removable with disabling the major feature | arulselvan.m@intel.com |  | Not needed, drop. [ww10.5] Cannot drop these easily, build error [ww11.5] dropped with widi and multidisplay disabled
frameworks/base | 0043-PORT-FROM-MAIN-Telephony-Call-Status-Polling-framewo.patch | telephony | Removable | arun.ravindran@intel.com |  | Mail sent to Thierry Deleau, Bruno [ww10.5] dropped
frameworks/base | 0111-PORT-FROM-MAIN-Policy-Handling-of-Network-Personaliz.patch | telephony | Removable | arun.ravindran@intel.com |  | Mail sent to Thierry Deleau, Bruno [ww10.5] dropped
frameworks/base | 0112-PORT-FROM-MAIN-Telephony-Enabling-Network-Personaliz.patch | telephony | Removable | arun.ravindran@intel.com |  | Mail sent to Thierry Deleau, Bruno [ww10.5] dropped
frameworks/base | 0114-PORT-FROM-MAIN-Telephony-Add-suspend-resume-and-MS-c.patch | telephony | Non-removable | arun.ravindran@intel.com |  | Mail sent to Thierry Deleau, Bruno
frameworks/base | 0115-PORT-FROM-MAIN-Telephony-Adding-OEM-HOOK-Constants.patch | telephony | Non-removable | arun.ravindran@intel.com |  | Mail sent to Thierry Deleau, Bruno
frameworks/base | 0135-PORT-FROM-MAIN-telephony-Add-IOemTelephony-and-Oem-s.patch | telephony | Non-removable | arun.ravindran@intel.com |  | Mail sent to Thierry Deleau, Bruno
frameworks/base | 0252-PORT-FROM-R4.1-core-Move-new-resources-to-end-of-the.patch | telephony | Non-removable | arun.ravindran@intel.com |  | Mail sent to Thierry Deleau, Bruno [ww10.5] dropped because of dependency with other dropped patch in telephony domain but this is required in FT's opinion.
frameworks/base | 0253-PORT-FROM-R4.1-cat-create-CatService-on-config_cat_s.patch | telephony | Removable | arun.ravindran@intel.com |  | Mail sent to Thierry Deleau, Bruno [ww10.5] dropped
frameworks/base | 0263-PORT-FROM-R41-Telephony-fix-long-time-to-show-regist.patch | telephony | Removable | arun.ravindran@intel.com |  | Mail sent to Thierry Deleau, Bruno [ww10.5] dropped
frameworks/opt/telephony | 0012-PORT-FROM-MAIN-Telephony-Adding-HSPAP-HSPA-support-i.patch | telephony | Removable | arun.ravindran@intel.com |  | Mail sent to Thierry Deleau, Bruno [ww10.5] dropped
frameworks/opt/telephony | 0013-PORT-FROM-MAIN-Telephony-Add-support-for-RIL_UNSOL_O.patch | telephony | Non-removable | arun.ravindran@intel.com |  | Mail sent to Thierry Deleau, Bruno
frameworks/opt/telephony | 0040-PORT-FROM-MAIN-Telephony-Enabling-Network-Personaliz.patch | telephony | Removable | arun.ravindran@intel.com |  | Mail sent to Thierry Deleau, Bruno [ww10.5] dropped
frameworks/opt/telephony | 0051-PORT-FROM-MAIN-Telephony-Add-suspend-resume-and-MS-c.patch | telephony | Non-removable | arun.ravindran@intel.com |  | Mail sent to Thierry Deleau, Bruno
packages/apps/Phone | 0019-PORT-FROM-MAIN-Phone-Adding-support-for-OemTelephony.patch | telephony | Non-removable | arun.ravindran@intel.com |  | Mail sent to Thierry Deleau, Bruno
frameworks/opt/telephony | 0048-PORT-FROM-MAIN-telephony-Integration-of-SmartCard-AP.patch | nfc | Removable with disabling the major feature | sebastian.niciarz@intel.com |  | Not needed, drop. [ww11.4] Cannot drop these easily, build error, dropped with NFC HAL disabled
frameworks/base | 0077-PORT-FROM-MAIN-NFC-Patch-to-add-Nfc-Secure-Element-A.patch | nfc | Removable with disabling the major feature | sebastian.niciarz@intel.com |  | Not needed, drop. [ww11.4] Cannot drop these easily, build error, dropped with NFC HAL disabled
frameworks/base | 0119-PORT-FROM-MAIN-base-Integration-of-SmartCard-API-V2..patch | nfc | Removable with disabling the major feature | sebastian.niciarz@intel.com |  | Not needed, drop. [ww11.4] Cannot drop these easily, build error, dropped with NFC HAL disabled
packages/apps/MusicFX | 0001-NXP-Premium-Integrating-new-NXP-Premium-library.patch | NXP | Removable with disabling the major feature | manishx.assudani@intel.com |  | Not needed, drop. [ww11.4] Cannot drop these easily, build error, dropped with NFC HAL disabled
packages/apps/Nfc | 0001-PORT-FROM-MAIN-Patch-to-update-Secure-Element-Manage.patch | nfc | Removable with disabling the major feature | sebastian.niciarz@intel.com |  | Not needed, drop. [ww11.4] Cannot drop these easily, build error, dropped with NFC HAL disabled
packages/apps/Nfc | 0012-PORT-FROM-MAIN-The-NFC-ON-OFF-default-setting-now-cu.patch | nfc | Removable with disabling the major feature | sebastian.niciarz@intel.com |  | Not needed, drop. [ww11.4] Cannot drop these easily, build error, dropped with NFC HAL disabled
packages/apps/Phone | 0018-PORT-FROM-MAIN-Phone-Integration-of-SmartCard-API-V2.patch | nfc | Removable with disabling the major feature | sebastian.niciarz@intel.com |  | Not needed, drop. [ww11.4] Cannot drop these easily, build error, dropped with NFC HAL disabled
frameworks/base | 0073-Add-HDMI_SET_STATUS-Intent-for-HDMISetting.patch | GFX | Removable |  | marc.mao@intel.com tianyang.zhu@intel.co randy.xu@intel.com | Reverted in WW07, drop
frameworks/base | 0181-PORT-FROM-MAIN-frameworks-Report-right-battery-statu.patch | energy management | Removable |  | ramakrishna.pallala@intel.com richard.tang@intel.com pierre.tardy@intel.com jenny.tc@intel.com sylvain.centelles@intel.com | Drop
frameworks/base | 0183-PORT-FROM-MAIN-BatteryController-Align-battery-icon-.patch | energy management | Removable |  | ramakrishna.pallala@intel.com richard.tang@intel.com pierre.tardy@intel.com jenny.tc@intel.com sylvain.centelles@intel.com | drop
frameworks/base | 0039-PORT-FROM-MAIN-PORT-FROM-R4-Catch-all-the-stack-info.patch | debug | Removable |  | xiaobing.tu@intel.com alex.zuo@intel.com | post PDK [ww10.5] dropped with CrashReport disabled
frameworks/base | 0162-PORT-FROM-MAIN-Moving-dump-system-call-stack-after-J.patch | debug | Removable with disabling the major feature |  | linx.z.chen@intel.com alex.zuo@intel.com | post PDK [ww10.5] dropped with CrashReport disabled
frameworks/base | 0163-PORT-FROM-MAIN-Debug-ANR-Create-stack-trace-file-onl.patch | debug | Removable with disabling the major feature |  | dongxing.zhang@intel.com alex.zuo@intel.com | post PDK [ww10.5] dropped with CrashReport disabled
frameworks/base | 0058-PORT-FROM-MAIN-Enable-ALS-to-control-LED-when-Automa.patch | core io | Removable with disabling the major feature |  | leo.yan@intel.com alek.du@intel.com | Post PDK, buttons won't be lit. [ww10.5] dropped
frameworks/base | 0059-PORT-FROM-MAIN-OrientationListener-add-SENSOR_DELAY_.patch | core io | Removable |  | jian.d.li@intel.com alek.du@intel.com | Drop
frameworks/base | 0082-PORT-FROM-MAIN-UsbDeviceManager-add-support-for-USB-.patch | core io | Removable |  | hao.wu@intel.com richard.tang@intel.com jianwei.yang@intel.com | Drop
frameworks/base | 0004-PORT-FROM-MAIN-frameworks-extract-class-JNICameraCon.patch | camera | Removable with disabling the major feature |  | gang.a.hu@intel.com miguel.verdu@intel.com ukri.niemimuukko@intel.com timo.kaikumaa@intel.com arnaud.mandy@intel.com kai.vehmanen@intel.com jie.j.zhang@intel.com liang.l.yang@intel.com | Post PDK [ww12.2] dropped with IntelCamera and TestCamera disabled
frameworks/base | 0009-PORT-FROM-MAIN-VIBRA-Add-loading-of-the-vibrator-har.patch | audio-comms | Non-removable | david.wagner@intel.com |  | Post PDK, Vibrator will be n/f until post PDK. Trying to get Google to accept upstream for PDK.
frameworks/base | 0010-PORT-FROM-MAIN-PORT-FROM-R3-FM-Support-on-IHF-Borqs.patch | audio-comms | Removable with disabling the major feature | david.wagner@intel.com |  | Post PDK, FM radio will be n/f until post PDK [ww10.5] dropped
frameworks/base | 0011-PORT-FROM-MAIN-PORT-FROM-R3-FM-framework-adaptation-.patch | audio-comms | Removable with disabling the major feature | david.wagner@intel.com |  | Post PDK, FM radio will be n/f until post PDK [ww10.5] dropped
frameworks/base | 0012-PORT-FROM-MAIN-Audio-add-FM_RX-stream-type-into-fram.patch | audio-comms | Removable with disabling the major feature | david.wagner@intel.com |  | Post PDK, FM radio will be n/f until post PDK [ww10.5] dropped
frameworks/base | 0013-PORT-FROM-MAIN-Prohibited-modification-of-publicly-e.patch | audio-comms | Removable with disabling the major feature | david.wagner@intel.com |  | Post PDK, FM radio will be n/f until post PDK [ww10.5] dropped
frameworks/base | 0014-PORT-FROM-MAIN-PORT-FROM-R3-FM-setFmRxMode-should-re.patch | audio-comms | Removable with disabling the major feature | david.wagner@intel.com |  | Post PDK, FM radio will be n/f until post PDK [ww10.5] dropped
frameworks/base | 0015-PORT-FROM-MAIN-PORT-FROM-R3-audio-pass-the-volume-ke.patch | audio-comms | Removable with disabling the major feature | david.wagner@intel.com |  | Post PDK, FM radio will be n/f until post PDK [ww10.5] dropped
frameworks/base | 0016-PORT-FROM-MAIN-PORT-FROM-R3-FM-volume-does-not-chang.patch | audio-comms | Removable with disabling the major feature | david.wagner@intel.com |  | Post PDK, FM radio will be n/f until post PDK [ww10.5] dropped
frameworks/base | 0087-PORT-FROM-MAIN-AUDIO-Add-FM-record-defs-and-handle-d.patch | audio-comms | Removable with disabling the major feature | david.wagner@intel.com |  | Post PDK, FM radio will be n/f until post PDK [ww10.5] dropped
frameworks/base | 0021-PORT-FROM-MAIN-temporarily-disable-rotation-animatio.patch | video | Removable with disabling the major feature |  |  | [ww10.5] new after 0227 rebase. 21, 211, 301 ABSP dependency, multidisplay cannot be removed, build error [ww11.5] dropped with widi and multidisplay disabled
frameworks/base | 0211-WM-fix-HDMI-freeze-when-rotate-by-disabling-transiti.patch | video | Removable with disabling the major feature |  |  | [ww10.5] new after 0227 rebase. 21, 211, 301 ABSP dependency, multidisplay cannot be removed, build error [ww11.5] dropped with widi and multidisplay disabled
frameworks/base | 0301-Add-an-intent-to-set-the-screen-orientation-to-lands.patch | video | Removable with disabling the major feature |  |  | [ww10.5] new after 0227 rebase. 21, 211, 301 ABSP dependency, multidisplay cannot be removed, build error [ww11.5] dropped with widi and multidisplay disabled

## UNDER_HAL Patches
PROJECT/PATH | PATCH NAME | COMPONENT | CATEGORY | FT Contact | Proposed FT Contact | Comments
bionic/ | 0002-PORT-FROM-MAIN-Add-a-flag-control-that-PRIVATE-libm-.patch | bionic | UNDER HAL
bionic/ | 0004-Sync-kernel-headers-from-external-kernel-headers-for.patch | misc | UNDER HAL
bionic/ | 0005-bionic-Enabling-telephony-in-JB-4.2.patch | telephony | UNDER HAL
bionic/ | 0006-AUDIO-a1026.h-alignment-in-kernel-bionic-external-fo.patch | audio | UNDER HAL
bionic/ | 0009-PORT-FROM-MAIN-potential-buffer-overflow-threats-in-.patch | bionic | UNDER HAL
bionic/ | 0019-PORT-FROM-MAIN-Add-system-call-fallocate-support-in-.patch | bionic | UNDER HAL
bionic/ | 0021-PORT-FROM-MAIN-atomisp-Update-atomisp.h-from-kernel.patch | camera | UNDER HAL
bionic/ | 0023-PORT-FROM-MAIN-bionic-update-psb_drm.h-to-remove-TTM.patch | video | UNDER HAL
bionic/ | 0028-PORT-FROM-MAIN-atomisp-Update-atomisp-header-for-V4L.patch | camera | UNDER HAL
bionic/ | 0029-PORT-FROM-MAIN-UX-Add-some-variables-in-psb_drm.h-fo.patch | UX | UNDER HAL
bionic/ | 0031-Camera-Update-bionic-headers.patch | camera | UNDER HAL
bionic/ | 0035-PORT-FROM-r4.1-Change-bionic-libc-kernel-common-linu.patch | GFX | UNDER HAL
bionic/ | 0040-Bionic-Adding-new-modem-control-driver-kernel-header.patch | telephony | UNDER HAL
build/ | 0001-PORT-FROM-MAIN-build-target-update-for-the-ctp_nomod.patch | build | MISCELLANEOUS
build/ | 0002-PORT-FROM-MAIN-Generate-gzip-package-of-system.img.patch | build | MISCELLANEOUS
build/ | 0003-PORT-FROM-MAIN-clean-droidboot-recovery-platform-rel.patch | PUPDR | MISCELLANEOUS
build/ | 0004-PORT-FROM-MAIN-Adding-build-configuration-for-boot.b.patch | build | MISCELLANEOUS
build/ | 0010-Enable-merrifield-platform-support.patch | build | MISCELLANEOUS
build/ | 0012-BUILD-Use-consistent-search-depth.patch | build | MISCELLANEOUS
build/ | 0018-Split-to-multiple-bash-commands.patch | build | MISCELLANEOUS
build/ | 0019-PORT-FROM-JBMR0-Intel-C-C-compiler-support.patch | compiler | MISCELLANEOUS
dalvik/ | 0003-Dalvik-Port-FI-for-MR1.-Use-x86-atom-FI.patch | dalvik | UNDER HAL
device/common/ | 0009-Multidevice-support-BCM-vendor-specific-library-conf.patch | bt | UNDER HAL
device/common/ | 0010-Multivendor-support-adding-libbt-vendor-conf-for-x86.patch | bt | UNDER HAL
device/common/ | 0011-BT-TI-WLxx-integration-in-MR1.patch | bt | UNDER HAL
device/intel/nfc | 0001-Disable-NFC-HAL.patch | nfc | NEW ADDING
frameworks/av | 0020-PORT-FROM-MAIN-Awesomeplayer-Add-SEEK_COMPETE-event-.patch | video | UNDER HAL
frameworks/av | 0022-PORT-FROM-MAIN-libstagefright-allow-mp4-muxer-to-be-.patch | video | UNDER HAL
frameworks/av | 0026-PORT-FROM-MAIN-Add-ThreadedSource-to-Stagefright-fra.patch | video | UNDER HAL
frameworks/av | 0027-PORT-FROM-MAIN-To-enable-VP8-video-playback-on-Jelly.patch | video | UNDER HAL
frameworks/av | 0028-PORT-FROM-MAIN-libstagefright-enable-AVI-playback-on.patch | video | UNDER HAL
frameworks/av | 0029-PORT-FROM-MAIN-Audio-JBMR1-Enable-WMA9-audio-Decodin.patch | audio | UNDER HAL
frameworks/av | 0030-PORT-FROM-MAIN-PORT-FROM-R3-FM-framework-adaptation-.patch | audio-comms | UNDER HAL
frameworks/av | 0031-PORT-FROM-MAIN-Audio-manage-FM-Rx-playback-volume-in.patch | audio-comms | UNDER HAL
frameworks/av | 0032-PORT-FROM-MAIN-PORT-FROM-R3-FM-Support-on-IHF-Borqs.patch | audio-comms | UNDER HAL
frameworks/av | 0042-PORT-FROM-MAIN-libstagefright-port-WMV-related-patch.patch | video | UNDER HAL
frameworks/av | 0046-PORT-FROM-MAIN-libmediaplayerservice-Enhance-NuPlaye.patch | video | UNDER HAL
frameworks/av | 0048-PORT-FROM-MAIN-libstagefright-pass-down-playing-info.patch | video/GFX | UNDER HAL
frameworks/av | 0051-PORT-FROM-MAIN-Enable-VAVideoDecoder-as-thumbnail-ge.patch | video | UNDER HAL
frameworks/av | 0052-PORT-FROM-MAIN-Porting-to-JB-PreProc-accoustics-effe.patch | video | UNDER HAL
frameworks/av | 0054-PORT-FROM-MAIN-AudioFlinger-rework-of-remove_effect-.patch | audio | UNDER HAL
frameworks/av | 0066-PORT-FROM-MAIN-Jellybean-Enabling-AAC-ELD-decoding-s.patch | video | UNDER HAL
frameworks/av | 0068-PORT-FROM-MAIN-JB-Support-of-ALAC-Decoder.patch | video | UNDER HAL
frameworks/av | 0070-PORT-FROM-MAIN-CTP-Offload-TPV-DoubleTwist-Player-Ca.patch | audio | UNDER HAL
frameworks/av | 0074-PORT-FROM-MAIN-Audio-MW-Frameworks-base-offload-MP3-.patch | audio | UNDER HAL
frameworks/av | 0075-PORT-FROM-MAIN-DUT-reboot-on-pause-resume-for-5.1-ch.patch | audio | UNDER HAL
frameworks/av | 0084-PORT-FROM-MAIN-AUDIO-RhB-Add-Stream-Flags-key-to-set.patch | audio | UNDER HAL
frameworks/native | 0001-PORT-FROM-MAIN-native-add-intel-color-format.patch | video | UNDER HAL
frameworks/native | 0002-Change-the-framebuffer-format-to-BGRA-base-on-PVR-de.patch | GFX | UNDER HAL
frameworks/native | 0007-PORT-FROM-MAIN-temporarily-disable-rotation-animatio.patch | video | UNDER HAL
frameworks/native | 0014-Add-Display-scaling-interface-for-HDMISetting.patch | GFX | UNDER HAL
frameworks/native | 0017-PORT-FROM-MAIN-Work-around-dead-lock-in-SurfaceFling.patch | GFX | UNDER HAL
frameworks/native | 0018-SurfaceFlinger-Optimize-Rotation-Animation-on-Extern.patch | GFX | UNDER HAL
frameworks/native | 0023-PORT-FROM-MAIN-Add-VP8-index-type-support.patch | video | UNDER HAL
frameworks/native | 0025-PORT-FROM-JBMR0-Add-a-flag-OMX_INTEL_COLOR_FormatYUV.patch | video | UNDER HAL
frameworks/native | 0029-SurfaceFlinger-fix-HDMI-freeze-when-rotate-by-disabl.patch | GFX | UNDER HAL
hardware/intel/wrs_omxil_core | 0001-Avoid-addling-quirk-requires-loaded-to-idle-after-al.patch | video | NEW ADDING
hardware/libhardware | 0001-PORT-FROM-MAIN-Add-device-definitions-in-HAL-for-JB.patch | audio | UNDER HAL
hardware/libhardware | 0002-PORT-FROM-MAIN-VIBRA-Adapt-AOSP-default-vibrator-HAL.patch | audio-comms | UNDER HAL
hardware/libhardware | 0003-PORT-FROM-MAIN-PORT-FROM-R3-FM-support-in-IHF-Borqs.patch | audio-comms | UNDER HAL
hardware/libhardware | 0004-PORT-FROM-MAIN-Audio-manage-FM-Rx-playback-volume-in.patch | audio-comms | UNDER HAL
hardware/libhardware | 0005-PORT-FROM-MAIN-add-a-hint-to-notify-surfaceflinger-t.patch | GFX | UNDER HAL
hardware/libhardware | 0006-PORT-FROM-MAIN-LIBHW-initialization-of-defined-varia.patch | audio | UNDER HAL
hardware/libhardware | 0007-PORT-FROM-MAIN-AUDIO-RENASAS-Enable-AudioHAL-stub-fo.patch | audio-comms | UNDER HAL
hardware/libhardware | 0008-PORT-FROM-MAIN-Audio-MW-hardware-libhardware-offload.patch | audio | UNDER HAL
hardware/libhardware | 0009-PORT-FROM-MAIN-AUDIO-RhB-Add-Stream-Flags-key-to-set.patch | audio | UNDER HAL
hardware/libhardware | 0013-PORT-FROM-MAIN-UX-Add-a-interface-function-for-curso.patch | UX | UNDER HAL
hardware/libhardware | 0015-CTP-Offload-Adding-metadata-info-for-gapless-playbac.patch | audio | UNDER HAL
hardware/libhardware_legacy | 0001-PORT-FROM-MAIN-VIBRA-Remove-vibrator-AOSP-implementa.patch | audio-comms | UNDER HAL
hardware/libhardware_legacy | 0002-PORT-FROM-MAIN-PORT-FROM-R3-FM-support-on-IHF-Borqs.patch | audio-comms | UNDER HAL
hardware/libhardware_legacy | 0003-PORT-FROM-MAIN-FM-libhardware_legacy-changes-for-FM-.patch | audio-comms | UNDER HAL
hardware/libhardware_legacy | 0004-PORT-FROM-MAIN-Audio-manage-FM-Rx-playback-volume-in.patch | audio-comms | UNDER HAL
hardware/libhardware_legacy | 0005-PORT-FROM-MAIN-AUDIO-Add-a-new-strategy-for-streams-.patch | audio | UNDER HAL
hardware/libhardware_legacy | 0006-PORT-FROM-MAIN-Enable-Audio-HAL-in-Jelly-Bean.patch | audio | UNDER HAL
hardware/libhardware_legacy | 0008-PORT-FROM-MAIN-Audio-legacy-init-of-all-attributes-w.patch | audio | UNDER HAL
hardware/libhardware_legacy | 0009-PORT-FROM-MAIN-AUDIO-HAL-Restore-BT-A2DP-device-avai.patch | audio | UNDER HAL
hardware/libhardware_legacy | 0010-PORT-FROM-MAIN-AUDIO-When-setting-a-null-device-for-.patch | audio | UNDER HAL
hardware/libhardware_legacy | 0012-PORT-FROM-MAIN-AUDIO-RENASAS-Enable-AudioHAL-stub-fo.patch | audio-comms | UNDER HAL
hardware/libhardware_legacy | 0013-PORT-FROM-MAIN-Revert-AUDIO-Select-Widi-output-devic.patch | widi | UNDER HAL
hardware/libhardware_legacy | 0016-PORT-FROM-MAIN-AUDIO-Add-FM-source-and-device-in-aud.patch | audio-comms | UNDER HAL
hardware/libhardware_legacy | 0017-PORT-FROM-MAIN-AUDIO-Add-a-new-strategy-STRATEGY_FM_.patch | audio-comms | UNDER HAL
hardware/libhardware_legacy | 0018-PORT-FROM-MAIN-AUDIO_FM-Add-forced-usage-support-for.patch | audio-comms | UNDER HAL
hardware/libhardware_legacy | 0039-AUDIO-Add-implementation-of-FM-Rx-volume-check-and-s.patch | audio-comms | UNDER HAL
hardware/ril | 0001-PORT-FROM-MAIN-ril-Enabling-telephony-in-JB-4.2.patch | telephony | UNDER HAL
hardware/ril | 0002-PORT-FROM-MAIN-ril-Enabling-seek-and-Smart-Card-API-.patch | nfc | UNDER HAL
hardware/ti/wlan | 0001-wifi-TI-MCP-2.5.4-integration.patch | wifi | UNDER HAL
hardware/ti/wlan | 0002-wifi-MCP-2.5.4-performances-improvements.patch | wifi | UNDER HAL
hardware/ti/wlan | 0003-wifi-TI-NLCP-R4-SP2-integration.patch | wifi | UNDER HAL
hardware/ti/wlan | 0004-wifi-TI-R5.018-Integration-and-rebase.patch | wifi | UNDER HAL
hardware/ti/wlan | 0005-WIFI-Move-calibration-file-to-factory.patch | wifi | UNDER HAL
hardware/ti/wlan | 0006-wifi-Send-a-scan-complete-to-mac-layer-when-cancel-s.patch | wifi | UNDER HAL
hardware/ti/wlan | 0007-wifi-add-missing-wake-up-queues-when-suspend-fails.patch | wifi | UNDER HAL
hardware/ti/wlan | 0008-Revert-wlan-set-default-wifi-regulatory-domain-v2.patch | wifi | UNDER HAL
hardware/ti/wlan | 0009-widi-Change-rcu-synchronization-to-remove-ADD_BEACON.patch | wifi | UNDER HAL
hardware/ti/wlan | 0010-WLAN-R5-Integration-cleanup-after-code-review.patch | wifi | UNDER HAL
hardware/ti/wlan | 0011-WLAN-Need-to-remove-dependency-on-.git-for-generatin.patch | wifi | UNDER HAL
hardware/ti/wlan | 0012-Revert-WIFI-Move-calibration-file-to-factory.patch | wifi | UNDER HAL
hardware/ti/wlan | 0013-wl12xx-use-request_firmware_nowait-unstead-of-reques.patch | wifi | UNDER HAL
hardware/ti/wlan | 0014-WLAN-fix-provisioning-issue-when-change-MAC-address-.patch | wifi | UNDER HAL
hardware/ti/wlan | 0015-WLAN-calibrator-add-stderr-outputs-to-aplogs.patch | wifi | UNDER HAL
hardware/ti/wlan | 0016-WLAN-Immediate-authentication-on-beacon-IE.patch | wifi | UNDER HAL
hardware/ti/wlan | 0017-Revert-PORT-FROM-R3-WLAN-fix-provisioning-issue-when.patch | wifi | UNDER HAL
hardware/ti/wlan | 0018-WLAN-fix-provisioning-issue-when-change-MAC-address-.patch | wifi | UNDER HAL
hardware/ti/wlan | 0019-wl12xx-release-wake-lock-when-removing-the-interface.patch | wifi | UNDER HAL
hardware/ti/wlan | 0020-compat-Add-early_suspend-support-needed-by-Android.patch | wifi | UNDER HAL
hardware/ti/wlan | 0021-Revert-Revert-WIFI-Move-calibration-file-to-factory.patch | wifi | UNDER HAL
hardware/ti/wlan | 0022-WLAN-SleepPolicy-Periodic-scan-integration.patch | wifi | UNDER HAL
hardware/ti/wlan | 0023-TI-R5.00.21-intergration.patch | wifi | UNDER HAL
hardware/ti/wlan | 0024-WLAN-Skip-bind-unbind-when-no-Wi-Fi-module-present.patch | wifi | UNDER HAL
hardware/ti/wlan | 0025-wifi-TI-R5.00.21-fix-TI-R5.00.21-version.patch | wifi | UNDER HAL
hardware/ti/wlan | 0026-Revert-WLAN-Skip-bind-unbind-when-no-Wi-Fi-module-pr.patch | wifi | UNDER HAL
hardware/ti/wlan | 0027-Revert-Revert-WLAN-Skip-bind-unbind-when-no-Wi-Fi-mo.patch | wifi | UNDER HAL
hardware/ti/wlan | 0028-HEADER-Include-kconfig.h-instead-of-autoconf.h.patch | wifi | UNDER HAL
hardware/ti/wlan | 0029-WLAN-add-Free-Running-RSSI-measurement.patch | wifi | UNDER HAL
hardware/ti/wlan | 0030-wl12xx-Log-the-packets-that-caused-WiFi-to-wake-up-t.patch | wifi | UNDER HAL
hardware/ti/wlan | 0031-wlan-Fix-div-by-0.patch | wifi | UNDER HAL
hardware/ti/wlan | 0032-wifi-failed-to-scan-if-recovery-during-scan-happens.patch | wifi | UNDER HAL
hardware/ti/wlan | 0033-Revert-PORT-FROM-R3-compat-Add-early_suspend-support.patch | wifi | UNDER HAL
hardware/ti/wlan | 0034-Wifi-Add-robustness-to-calibration-phase.patch | wifi | UNDER HAL
hardware/ti/wlan | 0035-wifi-Revert-wifi-increase-ps_poll_timeouts.patch | wifi | UNDER HAL
hardware/ti/wlan | 0036-wl12xx-avoid-removing-the-sdio-driver-while-loading-.patch | wifi | UNDER HAL
hardware/ti/wlan | 0037-wifi-wl12xx-Always-pass-DMA-able-buffers-to-mmc-func.patch | wifi | UNDER HAL
hardware/ti/wlan | 0038-wifi-mac80211-fix-ADDBA-declined-after-suspend-with-.patch | wifi | UNDER HAL
hardware/ti/wlan | 0039-wl12xx-add-support-for-U-APSD-powersave-for-Voice-tr.patch | wifi | UNDER HAL
hardware/ti/wlan | 0040-wl12xx-Always-log-the-packets-that-caused-WiFi-to-wa.patch | wifi | UNDER HAL
hardware/ti/wlan | 0041-wifi-balance-calls-to-list_add-list_del-if-interface.patch | wifi | UNDER HAL
hardware/ti/wlan | 0042-CUSTOM_BOARD-to-TARGET_DEVICE.patch | wifi | UNDER HAL
hardware/ti/wlan | 0043-wifi-prevent-add-interface-while-calibrating.patch | wifi | UNDER HAL
hardware/ti/wlan | 0044-wifi-check-if-interface-is-up-before-calibrating.patch | wifi | UNDER HAL
hardware/ti/wlan | 0045-wifi-ease-debugging-by-changing-pr_debug-with-pr_inf.patch | wifi | UNDER HAL
hardware/ti/wlan | 0046-wifi-prevent-reading-wlan-chip-register-when-FW-reco.patch | wifi | UNDER HAL
hardware/ti/wlan | 0047-wifi-display-allowed-multicast-address-list.patch | wifi | UNDER HAL
hardware/ti/wlan | 0048-calibrator-fix-klocwork-issues.patch | wifi | UNDER HAL
hardware/ti/wlan | 0049-wifi-multi-vendor-enabling-in-mainline.patch | wifi | UNDER HAL
hardware/ti/wlan | 0050-wifi-prevent-sdio-bus-access-if-driver-is-suspended.patch | wifi | UNDER HAL
hardware/ti/wlan | 0051-wl12xx-flush-the-workqueue-during-__ieee80211_suspen.patch | wifi | UNDER HAL
hardware/ti/wlan | 0052-wl12xx-Wait-for-pending-thread-irq-before-suspend-th.patch | wifi | UNDER HAL
hardware/ti/wlan | 0053-wl12xx-Fix-memleak-in-wl1271_acx_init_mem_config.patch | wifi | UNDER HAL
hardware/ti/wlan | 0054-wifi-show-callstack-on-sdio-access-during-suspend.patch | wifi | UNDER HAL
hardware/ti/wlan | 0055-calibrator-fix-klocwork-issues.patch | wifi | UNDER HAL
hardware/ti/wlan | 0056-REVERT-ME-Disable-the-building-process-for-hardware-.patch | wifi | UNDER HAL
hardware/ti/wlan | 0057-wifi-JB-MR1-Bring-Up-revert-REVERT-ME-Disable-the-bu.patch | wifi | UNDER HAL
hardware/ti/wlan | 0058-wifi-JB-MR1-Bring-Up-REVERT-ME-temporarily-relocate-.patch | wifi | UNDER HAL
hardware/ti/wlan | 0059-BUILD-Allow-customers-to-use-their-own-product-devic.patch | wifi | UNDER HAL
hardware/ti/wlan | 0060-Revert-wifi-JB-MR1-Bring-Up-REVERT-ME-temporarily-re.patch | wifi | UNDER HAL
hardware/ti/wlan | 0061-PORT-FROM-MR0-wl12xx-register-free-sdio-interrupt-wh.patch | wifi | UNDER HAL
hardware/ti/wlan | 0062-Wi-Fi-calibrator-Print-errno-content-if-NVS-file-cre.patch | wifi | UNDER HAL
hardware/ti/wlan | 0063-wifi-enable-CONFIG_MAC80211_DEBUGFS-support.patch | wifi | UNDER HAL
hardware/ti/wlan | 0064-wl12xx-reduce-tx_watchdog_timeout-to-2-secs.patch | wifi | UNDER HAL
hardware/ti/wlan | 0065-WIFI-PATCH-2-2-Move-gpio-resource-allocation-from-pl.patch | wifi | UNDER HAL
hardware/ti/wlan | 0066-PORT-FROM-JBMR0-wifi-mac80211-stop-Rx-during-HW-reco.patch | wifi | UNDER HAL
hardware/ti/wlan | 0067-PORT-FROM-JBMR0-wifi-call-ieee80211_sched_scan_stopp.patch | wifi | UNDER HAL
hardware/ti/wlan | 0068-wl12xx-Fix-double-free_irq.patch | wifi | UNDER HAL
hardware/ti/wlan | 0069-wl12xx-Remove-unused-flag-for-recovery-pending.patch | wifi | UNDER HAL
hardware/ti/wlan | 0070-PORT-FROM-R3-wifi-rework-recovery-during-suspend-res.patch | wifi | UNDER HAL
hardware/ti/wlan | 0071-wl12xx-Reduce-command-timeout-from-2secs-to-250ms.patch | wifi | UNDER HAL
hardware/ti/wlan | 0072-wl12xx-Dead-code-removal-in-suspend-path.patch | wifi | UNDER HAL
hardware/ti/wlan | 0073-wl12xx-Fix-possible-panic-in-resume-path.patch | wifi | UNDER HAL
hardware/ti/wlan | 0074-PORT-FROM-JBMR0-wl12xx-disable-elp-sleep-while-in-pl.patch | wifi | UNDER HAL
hardware/ti/wlan | 0075-wifi-ensure-Wifi-is-off-before-calibrating.patch | wifi | UNDER HAL
hardware/ti/wlan | 0076-PORT-FROM-JBMR0-wl12xx-remove-useless-wakelock.patch | wifi | UNDER HAL
hardware/ti/wlan | 0077-wlan-fix-klocwork-issues.patch | wifi | UNDER HAL
system/core | 0001-PORT-FROM-MAIN-Integrate-logcat-for-recovery-OS-in-J.patch | PUPDR | UNDER HAL
system/core | 0002-PORT-FROM-MAIN-REVERT-ME-add-LOGD-V-W-E-supprot-for-.patch | misc | MISCELLANEOUS
system/core | 0004-PORT-FROM-MAIN-FM-add-FM-mode-in-sytem-core-audio.h.patch | audio-comms | UNDER HAL
system/core | 0005-PORT-FROM-MAIN-Audio-Add-FM-RX-stream-type-in-audio-.patch | audio-comms | UNDER HAL
system/core | 0013-PORT-FROM-MAIN-Expand-variables-on-mount_all-command.patch | misc | MISCELLANEOUS
system/core | 0020-PORT-FROM-MAIN-AUDIO-Add-device-for-FM-record-in-aud.patch | audio-comms | UNDER HAL
system/core | 0023-PORT-FROM-MAIN-Audio-MW-system-core-codec-offload-fl.patch | audio | UNDER HAL
system/core | 0031-PORT-FROM-MAIN-UEVENTD-dev-mdmTRace-rights-should-be.patch | telephony | UNDER HAL
system/core | 0039-PORT-FROM-MAIN-AMTL-ttyACM-and-ttyPTI-rights-should-.patch | telephony | UNDER HAL
system/core | 0045-ueventd-provide-right-access-to-tty-for-telephony-co.patch | telephony | UNDER HAL
system/core | 0054-Modem-control-driver-Modifying-right-access-on-devic.patch | telephony | UNDER HAL
system/core | 0055-uevent-ttyIFXO-node-permission.patch | telephony | UNDER HAL
system/core | 0056-Add-parsing-of-props.rc-in-init.patch | telephony | UNDER HAL
system/netd | 0001-PORT-FROM-MAIN-wifi-enable-SoftAP.patch | wifi | UNDER HAL
system/netd | 0002-PORT-FROM-MAIN-tethering-widi-Limit-DHCP-server-netw.patch | wifi | UNDER HAL
system/netd | 0003-PORT-FROM-MAIN-widi-Add-to-netd-some-widi-dhcp-capab.patch | wifi | UNDER HAL
system/netd | 0005-wifi-JB-MR1-Bring-Up-Soft-ap-bringUp.patch | wifi | UNDER HAL
system/netd | 0006-PORT-FROM-MAIN-wifi-multi-vendor-enabling-in-mainlin.patch | wifi | UNDER HAL
system/netd | 0009-Tethering-Fix-bad-inclusion-of-header-for-SoftApCont.patch | wifi | UNDER HAL
vendor/intel/clovertrail | 0001-Disable-LVSE.patch | audio | NEW ADDING
vendor/intel/clovertrail | 0002-Disable-customized-overlays.patch |  | NEW ADDING
vendor/intel/clovertrail | 0003-Disable-the-CrashReport-to-remove-debug-patches-whic.patch | debug | NEW ADDING
vendor/intel/clovertrail | 0004-Disable-mulitidisplay-and-widi.patch | video/GFX | NEW ADDING
vendor/intel/clovertrail | 0005-Disable-IntelCamera-and-TestCamera.patch | camera | NEW ADDING
vendor/intel/common | 0001-Disable-the-GMS.patch | AOSP | NEW ADDING
hardware/intel/PRIVATE/camera_extension | 0001-Disble-the-camera-extension-feature-if-no-jni-head-f.patch | camera | NEW ADDING
hardware/intel/libcamera2 | 0001-Pass-the-build-if-no-camera-extension-features.patch | camera | NEW ADDING

## PDK Enabling patches
PROJECT/PATH | PATCH NAME | COMPONENT | CATEGORY | FT Contact | Proposed FT Contact | Comments
vendor/intel/clovertrail | 0001-modify-config-for-redhookbay-pdk-build.patch |  |  |  |  | disable nfc,otapackage,droidboot,widi,multiplay display,OMXIL,music offload,fg_conf
vendor/intel/PRIVATE/apps/Camera | 0001-disable-camera1-and-camera2-app.patch | camera
vendor/intel/PRIVATE/apps/Gallery | 0001-disable-module-libjni_filtershow_filters2.patch | gallery
vendor/intel/Aware | 0001-disable-intel-aware.patch | aware
vendor/intel/common | 0001-modify-common-config-for-redhookbay-pdk-build.patch |  |  |  |  | disable checkapi,recovery,camera,chaabi,crashlog,wpa,ti
vendor/intel/common | 0002-Enable-GUI-for-PDK.patch | Gfx
vendor/intel/apps/SensorCal | 0001-disable-SensorCal-app.patch | IO sensor
vendor/intel/apps/VppSettings | 0001-disable-VppSetting-app.patch | Video
vendor/intel/apps/HdmiSettings | 0001-disable-HdmiSettings-app.patch | Gfx
hardware/libhardware_legacy | 0001-restore-legacy-vibrator-HAL.patch | Audio
hardware/intel/PRIVATE/mmgr | 0001-disable-mmgr-test.patch | telephony
hardware/intel/PRIVATE/platform_test | 0001-disable-platform-test.patch | System Test
hardware/intel/PRIVATE/parameter-framework | 0001-add-headfiles-for-audio-parameter-framework.patch | audio
hardware/intel/PRIVATE/cmfwdl/lib | 0001-disable-cmfwdl-library.patch | telephony
hardware/intel/libintelprov | 0001-disable-phone-flashtool.patch | debug
hardware/intel/cmfwdl/reference_application | 0001-disable-cmfwdl-reference_application.patch | telephony
device/intel/PRIVATE/log_infra | 0001-disable-phonemonitor-and-crashreport-apps.patch | debug
device/intel/PRIVATE/DRM/widevine | 0001-disable-DRM-widevine.patch | DRM
device/intel/nfc | 0001-disable-nfc-smartcardsetting-app.patch | nfc
device/intel/apps/OemTelephony | 0001-disable-OemTelephony-app.patch | telephony
external/SmartcardService | 0001-disable-SmartCardService-app.patch | nfc

## Features
Feature Team | Feature | Google AOSP + Intel ABSP + Patch Set | PDK + Intel ABSP + Patch set | Comment
Gfx |  |  |  |  | Key:
| GUI | OK | OK |  |  | Green | Expected to work in PDK, no further changes required
| Image Display, Photo editor | OK | OK |  |  | Yellow | Requires above the HAL changes to work. Rework required
| Screen snapshot | OK | Not in PDK |  |  | Red | This feature is not yet working
Touch |  | OK | OK
Audio
| Keytones | OK | OK
| Ringtone | OK | OK
| Vibrator | OK | KO | Requires above the HAL changes, needs rework
| Playback | OK | OK
| Capture | OK | KO
| Concurrent playback and capture | OK | KO
| CSV call | OK | KO
Video
| Video playback | OK | OK
| Video Record | OK | KO
Telephony
| Voice Call MO MT | OK | KO | Requires above the HAL changes, needs rework
| SMS MO MT | OK | KO | Requires above the HAL changes, needs rework
| MMS | OK | KO | Requires above the HAL changes, needs rework
| Browsing (browser) | OK | KO | Requires above the HAL changes, needs rework
| SIM PIN: | OK | KO | Requires above the HAL changes, needs rework
| FDN: | OK | KO | Requires above the HAL changes, needs rework
| SIM Contacts | OK | KO | Requires above the HAL changes, needs rework
| STK (Basic usage) | OK | KO | Requires above the HAL changes, needs rework
| Airplane Mode | KO | KO
| SIM Hotswap | KO | KO | Not required for Day Zero Beta
CWS
| Wifi | OK | Partially OK
| BT | OK | Partially OK
| NFC | OK | KO | Requires above the HAL changes, needs rework
Camera Image
| Preview | OK | KO
| Still image | OK | KO
Charging |  | OK | OK
Debug
| Adb | OK | OK
USB
| Adb | OK | OK
| File exchange | OK | Not in PDK
GPS |  | KO | KO
Security |  | KO | KO | Not required for Day Zero Beta
DRM |  | KO | KO | Not required for Day Zero Beta
IO sensors storage |  | KO | KO | Untested